## Baseline
| Start | Weeks | [10 empty] | Milestone | Description | Planned | Achieved
|  | Phase 1 - Project Preparation | Phase 2 - Project Execution | Phase 3 - Project Closeup | Milestone |  | Planned |  | Achieved on time |  | Achieved late |  |  | Project start | 2019-09-18
1.1 - Project Setup & Software Concept | 0 | 2 | 0 | 0 |  | M1.1 - Scope Reviw |  | (2-Oct) |  | (2-Oct) |  |  | M1.1 | Scope Reviw | 2019-10-02 | 2019-10-02
1.2 - Project Planning | 2 | 4 | 0 | 0 |  | M1.2 - Plan Review |  | (30-Oct) |  | (30-Oct) |  |  | M1.2 | Plan Review | 2019-10-30 | 2019-10-30
2.1 - Requirements Specification | 6 | 0 | 2 | 0 |  | M2.1 - Software Requirements Review |  | (13-Nov) |  |  |  | (14-Nov) | M2.1 | Software Requirements Review | 2019-11-13 | 2019-11-14
2.2 - Software Development | 8 | 0 | 4 | 0 |  | M2.2 - Design Review |  | (11-Dec) |  |  |  |  | M2.2 | Design Review | 2019-12-11
2.3 - Software Acceptance and Review | 12 | 0 | 1 | 0 |  | M2.3 - Acceptance Review |  | (18-Dec) |  |  |  |  | M2.3 | Acceptance Review | 2019-12-18
3.1 - Project Closeup | 13 | 0 | 0 | 1 | 0 | M3.1 - Closeup | 0 | (8-Jan) | 0 |  | 0 |  | M3.1 | Closeup | 2020-01-08
Formulas:
Planned = [Planned, row above]+([Weeks]+[Phase 2 - Project Execution]+[Phase 3 - Project Closeup])*7
Planned = [Planned, row above]+([Weeks]+[Phase 2 - Project Execution]+[Phase 3 - Project Closeup])*7+14
Achieved = [Planned]
Achieved = [Planned]+1