## Deliverables
Deliverables | [5 empty] | 0 draft 1 revision 14/15 published
Status | Deliverable | Name | Version | Date | Link (GDocs) | Link (Published)
Published | D1.1.1 | V&S - Vision & Scope | 2020-01-03 | 2019-10-03 | Documento Atual | Documento Publicado
Published | D1.1.2 | MR1.1 - Milestone Report | 2020-01-02 | 2019-09-30 | Documento Atual | Documento Publicado
Published | D1.2.1 | SDP - Software Development Plan | 2020-01-01 | 2019-10-20 | Documento Atual | Documento publicado
Published | D1.2.2 | QAP - Quality Assurance Plan | 2020-01-01 | 2019-10-20 | Documento Atual | Documento Publicado
Published | D1.2.3 | MR1.2 - Milestone Report | 2020-01-02 | 2019-10-24 | Documento Atual | Documento Publicado
Published | D2.1.1 | SRS - Software Requirements Specification | 1.0 | 2019-10-25 | Documento Atual | Documento Publicado
Published | D2.1.2 | RP - Risk Plan | 0.9 | 2019-10-29 | Documento Atual | Documento Publicado
Published | D2.1.3 | ATP - Acceptance Test Plan | 1.0 | 2019-10-19 | Documento Atual | Documento Publicado
Published | D2.1.4 | MR2.1 - Milestone Report | 0.3 | 2019-11-09 | Documento Atual | Documento Publicado
Published | D2.2.1 | SAD - Software Architecture & Design | 0.6 | 2019-11-13 | Documento Atual | Documento Publicado
Published | D2.2.2 | MR2.2 - Milestone Report | 0.4 | 2019-12-04 | Documento Atual | Documento Publicado
Published | D2.3.1 | ATR - Acceptance Test Report | 1.0 | 2019-12-19 | Documento Atual | Documento Publicado
Published | D2.3.2 | QAR - Quality Assessment Report | 0.3 | 2019-12-11 | Documento Atual | Documento Publicado
Published | D2.3.3 | MR2.3 - Milestone Report | 0.3 | 2019-12-11 | Documento Atual | Documento Publicado
Revision | D3.1.1 | PMA - Post-Mortem Analysis | 0.1 | 2019-12-18 | Documento Atual

## MeetingMinutes
Meeting Minutes | [5 empty] | 1 draft 0 revision 8/9 published
Status | Number | Date | Type | Description | Link (GDocs) | Link (Published)
Published | 1 | 2019-09-25 | Progress | Team Kick-off | Documento Atual | Documento Publicado
Published | 2 | 2019-10-02 | Progress | Meeting Minutes #2 | Documento Atual | Documento Publicado
Published | 3 | 2019-10-09 | Progress | Meeting Minutes #3 | Documento Atual | Documento Publicado
Published | 4 | 2019-10-14 | Progress | Meeting Minutes #4 | Documento Atual | Documento Publicado
Published | 5 | 2019-10-19 | Progress | Meeting Minutes #5 | Documento Atual | Documento Publicado
Published | 6 | 2019-10-30 | Progress | Meeting Minutes #6 | Documento Atual | Documento Publicado
Published | 7 | 2019-11-06 | Progress | Meeting Minutes #7 | Documento Atual | Documento Publicado
Published | 8 | 2019-11-13 | Progress | Meeting Minutes #8 | Documento Atual | Documento Publicado
Draft | 8 | 2019-11-14 | Progress | Meeting Minutes #9 | Documento Atual
Published | 9 | 2019-11-20 | Progress | Meeting Minutes #9 | Documento Atual | Documento Publicado
Published | 10 | 2019-11-27 | Progress | Meeting Minutes #10 | Documento Atual | Documento Publicado
Published | 11 | 2019-12-04 | Progress | Meeting Minutes #11 | Documento Atual | Documento Publicado
Published | 12 | 2019-12-11 | Progress | Meeting Minutes #12 | Documento Atual | Documento Publicado
Published | 13 | 2019-12-18 | Progress | Meeting Minutes #13 | Documento Atual | Documento Atual

## Support
Support | [5 empty] | 1 draft 0 revision 8/9 published
Status | Type | Name | Version | Date | Link (GDocs) | Link (Published)
Published | Report | Team Log | 1.0 | 2019-09-25 | Documento | Documento Publicado
Published | Presentation | DashBoard | 2.0 | 2019-09-25 | Dashboard Atual | Dashboard Publicado
Published | Report | Project Estimation Report #1 | 0.3 | 2019-10-07 | Documento Atual | Dashboard Publicado
Published | Report | Earned Value Analysis | 0.2 | 2019-10-17 | Documento Atual | Documento Publicado
Published | Design | Baseline Plan | 0.0 | 2019-10-19 | Documento Atual | Documento Publicado
Published | Report | Tabela de Entregas | 2019-01-01 | 2019-10-19 | Documento Atual | Documento Publicado
Published | Presentation | Convenções de Código | 0.1 | 2019-10-19 | Documento Atual | Documento Publicado
Published | Presentation | KOM | 0.1 | 2019-10-29 | Documento Atual | Documento Publicado
Draft | Presentation | KOM |  |  | Documento Atual
Published | Report | Descriminação das tarefas do WBS | 0.2 | 2019-10-29 | Documento atual | Documento Publicado
Draft | Report | Relatório de Questionário aos Utilizadores | 0.1 | 2019-12-14 | Documento Atual