## Gantt
GPS 2019/2020 SmartParking Earned Value Analysis |  |  | Budgeted Cost of Work (BCW) |  |  |  |  | Actual Cost of Work (ACW) |  |  |  | Earned Value Analysis | Calendar (weeks)
| Baselined schedule |  | Planned start | Planned complete | Start from previous start | Planned duration (weeks) | Estimated effort (hours) | Actual start | Actual complete | Actual effort (hours) | Actual value (hours) |  | 2019-10-30 | 2019-11-06 | 2019-11-13 | 2019-11-20 | 2019-11-27 | 2019-12-04 | 2019-12-11 | 2019-12-18
[13 empty] | 30-10-2019 | 06-11-2019 | 13-11-2019 | 20-11-2019 | 27-11-2019 | 04-12-2019 | 11-12-2019 | 18-12-2019 | 30-12-1899 | 30-12-1899 | 30-12-1899 | 30-12-1899 | 30-12-1899 | 30-12-1899
| Baseline 1 - KOM | 2019-10-31 | 2018-11-30 | 2018-12-18 |  | 7 | 140 |  |  |  |  | Budget at Completion (BAC) | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140
[12 empty] | Planned Value (PV) | 0 | 0 | 31 | 38 | 54 | 60 | 91 | 126
[12 empty] | Earned Value (EV) | 0 | 0 | 31 | 38 | 54 | 60 | 91 | 126
WBS | Live values |  | 2019-10-30 | 2019-12-18 |  | 7 | 126 | 2019-10-30 | 2019-11-13 | 133.5 | 126 | Actual Cost (AC) | 0 | 18 | 35.5 | 49 | 69.5 | 91.5 | 118 | 133.5
Stage | Task | Subtask | [9 empty] | Notes | 2019-10-30: Actual work expended (Mark with X when task completed)
2.1. SW Requirements Specification | D2.1.1 - SRS | Discussão | 2019-10-30 | 2019-11-13 |  | 2 | 5 | 2019-10-30 | 2019-11-13 | 3 | 5 | Primeiro draft do SRS | 2 | 1 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.1 - SRS | Casos de uso | 2019-10-30 | 2019-11-13 | 0 | 2 | 3 | 2019-10-30 | 2019-11-13 | 4.5 | 3 | Elaboração de um tópico do documento | 3 | 1.5 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.1 - SRS | Requisitos funcionais | 2019-10-30 | 2019-11-13 | 0 | 2 | 3 | 2019-10-30 | 2019-11-13 | 4 | 3 | Elaboração de um tópico do documento | 1 | 3 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.1 - SRS | Requisitos não funcionais | 2019-10-30 | 2019-11-13 | 0 | 2 | 1 | 2019-10-30 | 2019-11-13 | 1.5 | 1 | Elaboração de um tópico do documento | 1 | 0.5 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.1 - SRS | Mockups | 2019-10-30 | 2019-11-13 | 0 | 2 | 5 | 2019-10-30 | 2019-11-13 | 4.5 | 5 | Elaboração de um tópico do documento | 2 | 2.5 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.1 - SRS | Revisão | 2019-10-30 | 2019-11-20 | 0 | 3 | 1 | 2019-10-30 | 2019-11-20 | 4.5 | 1 | Revisão do SRS | 0.5 | 1 | 3 | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.2 - RP | Discussão | 2019-10-30 | 2019-11-13 | 0 | 2 | 2 | 2019-10-30 | 2019-11-13 | 2 | 2 | Primeiro draft do RP | 2 | 0 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.2 - RP | Limiar do Sucesso | 2019-10-30 | 2019-11-13 | 0 | 2 | 1 | 2019-10-30 | 2019-11-13 | 0.5 | 1 | Elaboração de um tópico do documento | 0.5 | 0 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.2 - RP | Lista de riscos | 2019-10-30 | 2019-11-13 | 0 | 2 | 2 | 2019-10-30 | 2019-11-13 | 2 | 2 | Elaboração de um tópico do documento | 2 | 0 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.2 - RP | Ações de mitigação | 2019-10-30 | 2019-11-13 | 0 | 2 | 2 | 2019-10-30 | 2019-11-13 | 2 | 2 | Elaboração de um tópico do documento | 2 | 0 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.2 - RP | Revisão | 2019-10-30 | 2019-11-13 | 0 | 2 | 1 | 2019-10-30 | 2019-11-13 | 0.5 | 1 | Revisão do RP | 0.5 | 0 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.3 - ATP | Discussão | 2019-10-30 | 2019-11-13 | 0 | 2 | 1 | 2019-10-30 | 2019-11-13 | 1 | 1 | Primeiro draft do ATP | 0 | 1 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.3 - ATP | Estratégias | 2019-10-30 | 2019-11-13 | 0 | 2 | 2 | 2019-10-30 | 2019-11-13 | 0.5 | 2 | Elaboração de um tópico do documento | 0 | 0.5 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.3 - ATP | Estados base | 2019-10-30 | 2019-11-20 | 0 | 3 | 3 | 2019-10-30 | 2019-11-20 | 3.5 | 3 | Elaboração de um tópico do documento | 0.5 | 2 | 1 | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.3 - ATP | Casos de testes | 2019-10-30 | 2019-11-20 | 0 | 3 | 3 | 2019-10-30 | 2019-11-20 | 4 | 3 | Elaboração de um tópico do documento | 1 | 2 | 1 | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.3 - ATP | Matriz de testes | 2019-10-30 | 2019-11-13 | 0 | 2 | 1 | 2019-10-30 | 2019-11-13 | 0.5 | 1 | Elaboração de um tópico do documento | 0 | 0.5 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.3 - ATP | Revisão | 2019-10-30 | 2019-11-13 | 0 | 2 | 1 | 2019-10-30 | 2019-11-13 | 1 | 1 | Revisão do ATP | 0 | 1 | x | x | x | x | x | x | x | x | x | x | x | x
2.1. SW Requirements Specification | D2.1.4 - MR2.1 | Elaboração | 2019-11-06 | 2019-11-13 | 1 | 1 | 1 | 2019-11-06 | 2019-11-13 | 1 | 1 | Elaboração do MR2.1 | [8 empty] | x | x | x | x | x | x | bar: 2019-11-06 to 2019-12-18
2.2. SW Development | D2.2.1 - SAD | Discussão | 2019-11-13 | 2019-11-27 | 2 | 2 | 5 | 2019-11-13 | 2019-11-27 | 3 | 5 | Primeiro draft do SAD |  |  | 1 | 2 | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | D2.2.1 - SAD | Elaboração | 2019-11-13 | 2019-12-04 | 0 | 3 | 5 | 2019-11-13 | 2019-12-04 | 5.5 | 5 | Elaboração de todos os tópico do documento |  |  | 4 | 1 | 0.5 | x | x | x | x | x | x | x | x | x
2.2. SW Development | D2.2.1 - SAD | Revisão | 2019-11-13 | 2019-12-04 | 0 | 3 | 1 | 2019-11-13 | 2019-12-04 | 1 | 1 | Revisão do SAD |  |  | 0.5 | 0 | 0.5 | x | x | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Back-end | Base de dados | 2019-11-13 | 2019-11-27 | 0 | 2 | 5 | 2019-11-13 | 2019-11-27 | 5 | 5 | Back-end |  |  | 2 | 3 | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Back-end | Comunicação base de dados/aplicação | 2019-11-13 | 2019-12-11 | 0 | 4 | 8 | 2019-11-13 | 2019-12-11 | 9 | 8 | Back-end |  |  | 1 | 3 | 3 | 2 | x | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Back-end | Funcionalidade adicionar/remover veículos | 2019-11-20 | 2019-11-27 | 1 | 1 | 1 | 2019-11-20 | 2019-11-27 | 1 | 1 | Back-end | [8 empty] | x | x | x | x | x | x | bar: 2019-11-20 to 2019-12-18
2.2. SW Development | Desenvolvimento Back-end | Funcionalidade consulta | 2019-11-20 | 2019-11-27 | 0 | 1 | 2 | 2019-11-20 | 2019-11-27 | 1 | 2 | Back-end | [8 empty] | x | x | x | x | x | x | bar: 2019-11-20 to 2019-12-18
2.2. SW Development | Desenvolvimento Back-end | Funcionalidade estatísticas | 2019-11-20 | 2019-11-27 | 0 | 1 | 0 | 2019-11-20 | 2019-11-27 | 0.5 | 0 | Back-end |  |  |  | 0.5 | x | x | x | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Back-end | Funcionalidade pedidos administrador | 2019-11-20 | 2019-11-27 | 0 | 1 | 3 | 2019-11-20 | 2019-11-27 | 1 | 3 | Back-end | [8 empty] | x | x | x | x | x | x | bar: 2019-11-20 to 2019-12-18
2.2. SW Development | Desenvolvimento Back-end | Funcionalidade pedidos utilizador | 2019-11-27 | 2019-12-11 | 1 | 2 | 8 | 2019-11-27 | 2019-12-11 | 12 | 8 | Back-end | 2019-11-27: 4; 2019-12-04: 8; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Back-end | Teste | 2019-11-27 | 2019-12-11 | 0 | 2 | 8 | 2019-11-27 | 2019-12-11 | 7 | 8 | Testar o Back-end | 2019-11-27: 2; 2019-12-04: 5; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Front-end | Funcionalidade adicionar | 2019-11-27 | 2019-12-11 | 0 | 2 | 0 | 2019-11-27 | 2019-12-11 | 0 | 0 | Front-end | 2019-11-27: 0; 2019-12-04: 0; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Front-end | Funcionalidade editar | 2019-11-27 | 2019-12-18 | 0 | 3 | 1 | 2019-11-27 | 2019-12-18 | 8 | 1 | Front-end | 2019-11-27: 2; 2019-12-04: 4; 2019-12-11: 2; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Front-end | Funcionalidade remover | 2019-11-27 | 2019-12-11 | 0 | 2 | 1 | 2019-11-27 | 2019-12-11 | 2 | 1 | Front-end | 2019-11-27: 2; 2019-12-04: 0; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Front-end | Separador consulta | 2019-11-20 | 2019-12-18 | -1 | 4 | 5 | 2019-11-20 | 2019-12-18 | 8 | 5 | Front-end |  |  |  | 2 | 2 | 2 | 2 | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Front-end | Separador pedidos | 2019-11-20 | 2019-12-18 | 0 | 4 | 3 | 2019-11-20 | 2019-12-18 | 5 | 3 | Front-end |  |  |  | 1 | 1 | 1 | 2 | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Front-end | Separador estatisticas | 2019-11-20 | 2019-12-11 | 0 | 3 | 0 | 2019-11-20 | 2019-12-11 | 2 | 0 | Front-end |  |  |  | 1 | 1 | 0 | x | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Front-end | Interface utilizador | 2019-11-20 | 2019-12-11 | 0 | 3 | 5 | 2019-11-20 | 2019-12-11 | 10 | 5 | Front-end |  |  |  | 4 | 4 | 2 | x | x | x | x | x | x | x | x
2.2. SW Development | Desenvolvimento Front-end | Teste | 2019-12-04 | 2019-12-18 | 2 | 2 | 8 | 2019-12-04 | 2019-12-18 | 3 | 8 | Testar o Front-end | 2019-12-04: 2; 2019-12-11: 1; 2019-12-18: x | x | x | x | x | x | x
2.2. SW Development | D2.2.2 - MR2.2 | Elaboração | 2019-12-04 | 2019-12-11 | 0 | 1 | 1 | 2019-12-04 | 2019-12-11 | 0.5 | 1 | Elaboração do MR2.2 | 2019-12-04: 0.5; 2019-12-11: x; 2019-12-18: x | x | x | x | x | x | x
2.3. SW Acceptance and Delivery | D2.3.1 - ATR | Realização de testes | 2019-12-11 | 2019-12-18 | 4 | 1 | 3 | 2019-12-11 | 2019-12-18 | 2.5 | 3 | Testes da Aceitação | 2019-12-11: 2.5; 2019-12-18: x | x | x | x | x | x | x
2.3. SW Acceptance and Delivery | D2.3.1 - ATR | Elaboração | 2019-12-11 | 2019-12-18 | 0 | 1 | 2 | 2019-12-11 | 2019-12-18 | 1 | 2 | Elaboração de todos os tópico do documento | [8 empty] | x | x | x | x | x | x | bar: 2019-12-11 to 2019-12-18
2.3. SW Acceptance and Delivery | D2.3.1 - ATR | Revisão | 2019-12-11 | 2019-12-18 | 0 | 1 | 1 | 2019-12-11 | 2019-12-18 | 0.5 | 1 | Revisão do ATR | 2019-12-11: 0.5; 2019-12-18: x | x | x | x | x | x | x
2.3. SW Acceptance and Delivery | D2.3.2 - QAR | Realização de testes | 2019-12-11 | 2019-12-18 | 0 | 1 | 5 | 2019-12-11 | 2019-12-18 | 2 | 5 | Testes da Qualidade | 2019-12-11: 2; 2019-12-18: x | x | x | x | x | x | x
2.3. SW Acceptance and Delivery | D2.3.2 - QAR | Elaboração | 2019-12-11 | 2019-12-18 | 0 | 1 | 3 | 2019-12-11 | 2019-12-18 | 1 | 3 | Elaboração de todos os tópico do documento | [8 empty] | x | x | x | x | x | x | bar: 2019-12-11 to 2019-12-18
2.3. SW Acceptance and Delivery | D2.3.2 - QAR | Revisão | 2019-12-11 | 2019-12-18 | 0 | 1 | 1 | 2019-12-11 | 2019-12-18 | 0.5 | 1 | Revisão do QAR | 2019-12-11: 0.5; 2019-12-18: x | x | x | x | x | x | x
2.3. SW Acceptance and Delivery | D2.3.3 - MR2.3 | Elaboração | 2019-12-11 | 2019-12-18 | 0 | 1 | 3 | 2019-12-11 | 2019-12-18 | 1 | 3 | Elaboração do MR2.3 | [8 empty] | x | x | x | x | x | x | bar: 2019-12-11 to 2019-12-18
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
[10 empty] | 0 | 0
Formulas:
Budgeted Cost of Work (BCW) = IF(OR(ISBLANK(N2),ISBLANK([Stage])),"",OFFSET(N2,0,F10+MATCH([Budgeted Cost of Work (BCW), row above],N2:AA2,0)-1))
Budgeted Cost of Work (BCW) = IF(OR(ISBLANK(N2),ISBLANK([Stage])),"",OFFSET(N2,0,F27+MATCH(D10,N2:AA2,0)-1))
Actual Cost of Work (ACW) = iferror(index(N2:AA2,1,match(1,if(isnumber([Calendar (weeks)]:AA9),1,0),0)))

## Tables
Stage
2.1. SW Requirements Specification
2.2. SW Development
2.3. SW Acceptance and Delivery